## README
Template budget tracker. Tracks actual vs budeting spending.
This is based off fund expenditure report from SAP and can be adapted to other financial management systems
Sheets "Grants Summary" and "Spending" have to be manually updated, but everything else can be set up at the start of a project and will update automatically
This template assumes that there are two grants. If there is more than one donor / grant from a project, append the speding reports from all grants in the "Spending" sheet.
Classification: This uses alphanumberic codes to classify line items so that they can be easiy categorised. Some expenses (eg - Salary payments in this example) have to be manually inserted as these have default classification by the home institution and cannot be changed. These codes are established at the start of the project and are used in the description when classifying expenses.
This template assumes that the codes link to the line item in the funder budget. It may be useful to disaggrate costs further for tracking internally. This system makes that easy by adding more code - eg- if you want to split field costs by location .
This template only accounts for actual spend. It is important to also keep track or pending expdenditures - eg. equipment rental paid to the home institution / salaries for support staff.
Grants Summary | This sheet tracks the incoming funds from donors and exchange rates. When another tranche of funding comes in, this needs to be updated.
Spending | All spending on project to date. This is a fund download that is downloaded from the finance management system. This needs to be regularly updated (suggest every 2 months, or monthly during times of high spending)
Fields: Grant: Name of donor that can link to the donor name colum in the "Spending" sheet Fund no: fund classification on finance management system Description: Expenditure description captured in the finance management system Date: Date expense was assigned to fund Code: Expense category. This can be manually inputted or programmed (I use stata to extract the code or assign a code on expenses that I did not put on system - eg. default staff payment categorisation Amount: Value of expense in local currency
Field costs | This sheet tracks expenditure against the budget for field related costs. The budgeted amounts are the line items that have been approved by the funder The Spent section is generated from the "Spending" tab The Remaining section subtracts the spent from the budgeted amounts and highlight cells that are nearing or have exceded the budgeted amounts. If there are multple grants for a project, add columns for each grant.
Staff costs | This sheet tracks expenditure against the budget for staff related costs and mirrors the Field costs tab
Cash flow | This sheet shows a summary of how total received and spend, current amount in fund and total budget remaining

## Grants Summary
EXCHANGE RATES
|  | GBP | USD
| Budgeting exchange rate | 16.75 | 13
| Average exchange rate | 17.43 | 13.43
| Weighted exchange rate | 17.8967 | 13.43
| Current exchange rate | 17.2 | 13.1
| Conservative exchange rate | 16 | 12
Grant 1
|  | Status | Budget GBP | Budget ZAR | GBP receieved | ZAR receieved | Exchange rate | Proportion received | Weighted ER
Deliverables | Project summary | Received | 10000 | 167500 | 10000 | 160300 | 16.03 | 0.1087 | 5.3433
| Progress Report 1 | Received | 20000 | 335000 | 20000 | 376600 | 18.83 | 0.21739 | 12.5533
| Progress Report 2 | Pending | 20000 | 335000 |  |  |  | 0 | 0
| Progress Report 3 | Pending | 20000 | 335000 |  |  |  | 0 | 0
| Final report | Pending | 22000 | 368500 |  |  |  | 0 | 0
| Total |  | 92000 | 1541000 | 30000 | 536900
Grant 2
|  | Status | Budget USD | Budget ZAR | USD Receieved | ZAR receieved | Exchange rate | Proportion received | Weighted ER
Deliverables | Progress Report 1 | Received | 60000 | 780000 | 60000 | 805800 | 13.43 | 0.37267 | 13.43
| Progress Report 2 | Pending | 60000 | 780000
| Final report | Pending | 41000 | 533000
| Total |  | 161000 | 2093000 | 60000 | 805800
0

## Spending
GRANT | FUND NO | DESCRIPTION | CODE | DATE | AMOUNT | Notes
Grant 1 | 111111 | PINACLE/206EQU/LAPTOP-RA-DATA | 206EQU | 2019-01-02 | 22000
Grant 1 | 111111 | PINACLE/206EQU/LAPTOP-RA-FIELD | 206EQU | 2019-01-02 | 22000
Grant 1 | 111111 | PINACLE/206EQU/LAPTOP-RM | 206EQU | 2019-01-02 | 22000
Grant 1 | 111111 | UCT/206EQU/TABLET-RENTAL | 206EQU | 2019-01-02 | 10000
Grant 1 | 111111 | GRANT1-INCOME | GRANT | 2017-01-01 | -160300
Grant 1 | 111111 | GRANT1-INCOME | GRANT | 2017-06-01 | -376600
Grant 1 | 111111 | GRANT1-OVERHEAD | OVRHD | 2017-01-01 | 20908.69
Grant 1 | 111111 | GRANT1-OVERHEAD | OVRHD | 2017-06-01 | 49121.73
Grant 2 | 222222 | U0 Payroll Postings - August | 101LAB | 2019-01-28 | 4000
Grant 2 | 222222 | U0 Payroll Postings - August | 101LAB | 2017-06-27 | 1371.95
Grant 2 | 222222 | U0 Payroll Postings - August | 101LAB | 2017-07-11 | 2156.26
Grant 2 | 222222 | U0 Payroll Postings - August | 101LAB | 2017-08-22 | 9130.43
Grant 2 | 222222 | U0 Payroll Postings - December | 101LAB | 2017-12-19 | 23333.33
Grant 2 | 222222 | U0 Payroll Postings - December | 101LAB | 2017-12-19 | 140
Grant 2 | 222222 | U0 Payroll Postings - December | 101LAB | 2017-12-19 | 148.72
Grant 2 | 222222 | U0 Payroll Postings - January | 101LAB | 2018-01-22 | 148.72
Grant 2 | 222222 | U0 Payroll Postings - January | 101LAB | 2018-01-22 | 140
Grant 2 | 222222 | U0 Payroll Postings - January | 101LAB | 2018-01-22 | 233.33
Grant 2 | 222222 | U0 Payroll Postings - January | 101LAB | 2018-01-22 | 23333.33
Grant 2 | 222222 | U0 Payroll Postings - August | 102LAB | 2017-08-22 | 123.6
Grant 2 | 222222 | U0 Payroll Postings - August | 102LAB | 2017-08-22 | 32.3
Grant 2 | 222222 | U0 Payroll Postings - August | 102LAB | 2017-08-22 | 54.78
Grant 2 | 222222 | U0 Payroll Postings - September | 102LAB | 2017-09-19 | 148.72
Grant 2 | 222222 | U0 Payroll Postings - September | 102LAB | 2017-09-19 | 233.33
Grant 2 | 222222 | U0 Payroll Postings - September | 102LAB | 2017-09-19 | 23333.33
Grant 2 | 222222 | U0 Payroll Postings - September | 102LAB | 2017-09-19 | 140
Grant 2 | 222222 | U0 Payroll Postings - October | 102LAB | 2017-10-20 | 212.12
Grant 2 | 222222 | U0 Payroll Postings - October | 102LAB | 2017-10-20 | 148.72
Grant 2 | 222222 | U0 Payroll Postings - October | 102LAB | 2017-10-20 | 140
Grant 2 | 222222 | U0 Payroll Postings - October | 102LAB | 2017-10-20 | 21212.12
Grant 2 | 222222 | U0 Payroll Postings - November | 102LAB | 2017-11-21 | 23333.33
Grant 2 | 222222 | U0 Payroll Postings - November | 102LAB | 2017-11-21 | 148.72
Grant 2 | 222222 | U0 Payroll Postings - November | 102LAB | 2017-11-21 | 233.33
Grant 2 | 222222 | U0 Payroll Postings - November | 102LAB | 2017-11-21 | 140
Grant 2 | 222222 | U0 Payroll Postings - December | 102LAB | 2017-12-19 | 233.33
Grant 2 | 222222 | U0 Payroll Postings - February | 102LAB | 2017-07-11 | 107817.34
Grant 2 | 222222 | VENUE1/200FGS/VENUE-HIRE | 200FGS | 2017-08-22 | 10000
Grant 2 | 222222 | ABOUTTHYME/200FGS/FOOD | 200FGS | 2017-08-22 | 2452
Grant 2 | 222222 | CAFE/201MTG/WORKSHOP-PARTNER1-TOC | 201MTG | 2019-01-01 | 20000
Grant 2 | 222222 | CAFE/201MTG/WORKSHOP-PARTNER1-DESIGN | 201MTG | 2019-01-02 | 10000
Grant 2 | 222222 | EFT/202TRA/TRAIN-STIPEND-SURVEYORS | 202TRA | 2017-06-06 | 50000
Grant 2 | 222222 | ABOUTTHYME/200FGS/TRAIN-LUNCH | 202TRA | 2017-06-06 | 10000
Grant 2 | 222222 | GRANT2-INCOME | GRANT | 2017-06-01 | -805800
Grant 2 | 222222 | GRANT2-OVERHEAD | OVRHD | 2017-06-01 | 105104.3478
Grant 2 | 222222 | EFT/200FGS/TRANSPORT-PARTICIPANTS | 200FGS | 2017-08-22 | 2000
Grant 2 | 222222 | VENUE1/200FGS/VENUE-HIRE | 200FGS | 2017-02-02 | 10000
Grant 2 | 222222 | ABOUTTHYME/200FGS/FOOD | 200FGS | 2017-02-02 | 4000
Grant 2 | 222222 | EFT/200FGS/TRANSPORT-PARTICIPANTS | 200FGS | 2017-02-02 | 4000
Grant 2 | 222222 | VENUE1/200FGS/VENUE-HIRE | 200FGS | 2017-03-03 | 10000
Grant 2 | 222222 | ABOUTTHYME/200FGS/FOOD | 200FGS | 2017-03-03 | 4000
Grant 2 | 222222 | EFT/200FGS/TRANSPORT-PARTICIPANTS | 200FGS | 2017-03-03 | 4000

## Field Costs
| GBP | 17.8967 | Average actual received exchange rate to date | [7 empty] | Less than 10% of line item budget remaining
| USD | 13.43 | Average actual received exchange rate to date | [7 empty] | Less that 10% overspend on budget line item
More than 10% overspend on budget ine item
|  |  |  | Budget |  |  |  | Spent |  | Remaining
|  |  |  | Grant 1 |  | Grant 2 |  | Grant 1 | Grant 2 | Grant 1 | Grant 2
| Category | Code |  | GBP | ZAR | USD | ZAR | ZAR | ZAR | ZAR | ZAR
5. Field Costs | Focus groups | 200FGS |  |  | 0 | 4000 | 53720 | 0 | 50452 | 0 | 3268
5. Field Costs | Meetings | 201MTG |  |  | 0 | 4000 | 53720 | 0 | 30000 | 0 | 23720
5. Field Costs | Baseline Training | 202TRA |  |  | 0 | 4000 | 53720 | 0 | 60000 | 0 | -6280
5. Field Costs | Baseline Surveyor wage | 203SAL |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline Supervisor Wage | 204SAL |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline Backcheck wage | 205SAL |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline equipment rental | 206EQU |  | 4000 | 71586.6667 | 4000 | 53720 | 76000 | 0 | -4413.3333 | 53720
5. Field Costs | Baseline transport | 207TRP |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline communication | 208COM |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline printing and stationery | 209PRI |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline refreshements | 210REF |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Baseline translation | 211TLN |  | 4000 | 71586.6667 | 0 | 0 | 0 | 0 | 71586.6667 | 0
5. Field Costs | Baseline compensation | 212CPN |  | 4000 | 71586.6667 | 0 | 0 | 0 | 0 | 71586.6667 | 0
5. Field Costs | Endline Training | 213TRA |  | 0 | 0 | 4000 | 53720 | 0 | 0 | 0 | 53720
5. Field Costs | Endline Surveyor wage | 214SAL |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline Supervisor Wage | 215SAL |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline Backcheck wage | 216SAL |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline equipment rental | 217EQU |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline transport | 218TRP |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline communication | 219COM |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline printing and stationery | 220PRI |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline refreshements | 221REF |  | 4000 | 71586.6667 | 4000 | 53720 | 0 | 0 | 71586.6667 | 53720
5. Field Costs | Endline translation | 222TLN |  | 4000 | 71586.6667 | 0 | 0 | 0 | 0 | 71586.6667 | 0
5. Field Costs | Endline compensation | 223CPN |  | 4000 | 71586.6667 | 0 | 0 | 0 | 0 | 71586.6667 | 0
| Total | ZAR |  |  | 1431733.333 |  | 1074400 | 76000 | 140452 | 1355733.333 | 933948
|  | GBP |  | 80000 | [5 empty] | 75753.3991
|  | USD |  |  |  | 80000 |  |  |  |  | 69541.9211

## Staff Costs
GBP | 17.8967 | [7 empty] | Less than 10% of line item budget remaining
USD | 13.43 | [7 empty] | Less that 10% overspend on budget line item
More than 10% overspend on budget ine item
|  | Budget |  |  |  | Spent |  | Remaining
|  | Grant 1 |  | Grant 2 |  | Grant 1 | Grant 2 | Grant 1 | Grant 2
Category | Code | GBP | ZAR | USD | ZAR | ZAR | ZAR | ZAR | ZAR
Research Associate - Field | 101LAB |  | 0 | 10000 | 134300 | 0 | 64136.07 | 0 | 70163.93
Research Associate - Data | 102LAB |  | 0 | 10000 | 134300 | 0 | 177685.07 | 0 | -43385.07
Reasearch Manager | 103LAB |  | 0 | 10000 | 134300 | 0 | 0 | 0 | 134300
Grant Manager | 104LAB |  | 0 | 10000 | 134300 | 0 | 0 | 0 | 134300
Administrative Associate | 105LAB |  | 0 | 10000 | 134300 | 0 | 0 | 0 | 134300
Executive Director | 106LAB |  | 0 | 10000 | 134300 | 0 | 0 | 0 | 134300
Total | ZAR | 0 | 0 |  | 805800 | 0 | 241821.14 | 0 | 563978.86
GBP
| USD |  |  | 60000 |  |  |  |  | 41993.9583

## Cash Flow
|  | Grant 1 | Grant 2 |  | Notes
Total Budget |  | 1646493.333 | 2162230 |  | Total expected budget in local currency (total in foreign amount multiplied by average exchange rate to date)
Total received | GRANT | 536900 | 805800 |  | From Spending tab
Overhead paid | OVRHD | 70030.42 | 105104.3478 |  | From Spending tab
Total spent |  | 76000 | 382273.14 | 458273.14 | From field costs and staff costs tab
Remaining in fund |  | 390869.58 | 318422.5122 |  | Amount available in fund
Pending ZAR |  | 1109593.333 | 1356430 |  | Expected amount still to be paid by donor using average exchange rate to date
Pending overhead |  | 144729.5652 | 111998.8073 |  | Remaing overhead to be deducted and paid to host institution - Assumes overhead of 15% for Grant 1 and 9% for Grant 2.
Remaining budget |  | 1355733.348 | 1562853.705 | 2918587.053 | Total amount remainig to be spent
Checks remaining funds |  | -390869.58 | -318422.5122 |  | From Spending tab - This should be equal to the amounts in row 6. This check ensures that you haven't missed any expenses in field and staff costs
Checks balance |  | 0 | 0